## Handover Register
Construction Handover Register
21-section handover register template ¦ handoverpoint.com.au ¦ Free to use
Item | Description | Responsible Company | Required By | Status | Date Received | Verified By | Notes
1. General
1.1
1.2
2. Consultant Compliances & Statements
2.1
2.2
3. Certificates & Compliances
3.1
3.2
4. Operation & Maintenance Manuals
4.1
4.2
5. As-Builts
5.1
5.2
6. Warranties
6.1
6.2
7. Commissioning
7.1
7.2
8. Witness Testing
8.1
8.2
9. Technical Training
9.1
9.2
10. Defects Inspections Undertaken
10.1
10.2
11. Inspection Reports & Records
11.1
11.2
12. Authorities - Agreements & Offers
12.1
12.2
13. Maintenance
13.1
13.2
14. Registers
14.1
14.2
15. Master Schedules
15.1
15.2
16. Spares
16.1
16.2
17. Regulation 187 FRV Submission
17.1
17.2
18. OP Checklist
18.1
18.2
19. Building Permit Conditions
19.1
19.2
20. QA & ITPs
20.1
20.2
21. Practical Completion
21.1
21.2

## Instructions
How to use this Handover Register
This is the standard 21-section construction handover register used to track every deliverable a project owner needs before Practical Completion. Add one row per document or deliverable under the matching section, then update the status as items come in. No personal data is included; the register is yours to fill in.
Columns
Item | A reference number for the deliverable, e.g. 5.2. The first digit matches the section number.
Description | What the deliverable is, e.g. 'As-built drawings, mechanical services'.
Responsible Company | The subcontractor, consultant or supplier who owes the item.
Required By | The date the item is due, usually tied to a programme milestone or Practical Completion.
Status | Where the item is up to, e.g. Outstanding, Received, Under Review, Verified, Rejected.
Date Received | The date the document actually arrived.
Verified By | Who checked the item against the specification and accepted it.
Notes | Any comment: revision number, transmittal reference, or the reason an item was rejected.
The 21 handover sections
1. General | Front-matter and anything that does not sit neatly under another section.
2. Consultant Compliances & Statements | Design compliance statements signed off by the project consultants.
3. Certificates & Compliances | Statutory and product certificates confirming the works comply.
4. Operation & Maintenance Manuals | O&M manuals for installed plant, equipment and systems.
5. As-Builts | As-built drawings and models reflecting what was actually built.
6. Warranties | Manufacturer and installer warranties for materials and equipment.
7. Commissioning | Commissioning records for services and systems that were commissioned.
8. Witness Testing | Records of tests witnessed by the client, consultant or authority.
9. Technical Training | Evidence that the client's staff were trained on installed systems.
10. Defects Inspections Undertaken | Records of defect inspections carried out during the works.
11. Inspection Reports & Records | Inspection reports and supporting records across the trades.
12. Authorities - Agreements & Offers | Agreements and offers to connect from authorities and utilities.
13. Maintenance | Ongoing maintenance requirements and schedules handed to the client.
14. Registers | Asset, equipment and other registers required at handover.
15. Master Schedules | Master schedules that index the deliverables in the handover.
16. Spares | Spare parts and stock handed over to the client.
17. Regulation 187 FRV Submission | Fire safety documentation for the FRV submission under Regulation 187.
18. OP Checklist | Occupancy Permit checklist items required for handover.
19. Building Permit Conditions | Conditions attached to the building permit that must be discharged.
20. QA & ITPs | Quality assurance records and signed-off Inspection & Test Plans.
21. Practical Completion | Documents tied to reaching and certifying Practical Completion.
HandoverPoint
Generate this register automatically from your spec at handoverpoint.com.au