## Inspection & Test Plan
Inspection & Test Plan (ITP)
Construction ITP template ¦ handoverpoint.com.au ¦ Free to use
Activity / Task | Reference Spec Clause | Inspection / Test Required | Acceptance Criteria | Responsibility | Hold / Witness Point | Records Required | Status
Formwork inspection prior to concrete pour | AS 3610 / Spec 03 30 00 | Visual inspection of formwork alignment, dimensions and cleanliness | Formwork true to line and level within tolerance; no debris | Site Engineer | Hold Point | Signed inspection checklist, photos | Open
Concrete compressive strength test | AS 1379 / Spec 03 30 00 | 28-day cylinder compressive strength test | Characteristic strength meets specified grade (e.g. 32 MPa) | Testing Lab | Witness Point | NATA test certificate | Open

## Instructions
How to use this Inspection & Test Plan
An Inspection & Test Plan (ITP) sets out the checks and tests for a work activity, who does them, what counts as a pass, and which records to keep. Add one row per activity. The two greyed rows are worked examples, overwrite or delete them. Reference your own project specification clauses.
Columns
Activity / Task | The work being inspected or tested, e.g. 'Waterproofing to wet areas'.
Reference Spec Clause | The specification section or Australian Standard that sets the requirement.
Inspection / Test Required | The specific check or test to be performed.
Acceptance Criteria | What a pass looks like: the measurable or observable standard to be met.
Responsibility | Who carries out the inspection or test, e.g. Site Engineer, testing lab, subcontractor.
Hold / Witness Point | Hold Point: work must stop until signed off. Witness Point: a party may attend but work continues if they do not.
Records Required | The evidence to keep, e.g. checklist, NATA certificate, photographs.
Status | Where the item is up to, e.g. Open, Passed, Failed, Closed.
Hold points vs witness points
Hold Point | A mandatory stop. Work cannot proceed past this point until the nominated party has inspected and released it.
Witness Point | A notified point. The nominated party is invited to attend, but if they do not, work may continue.
HandoverPoint
Generate this register automatically from your spec at handoverpoint.com.au