## Sample Register
Sample & Submittal Register
Construction sample register template ¦ handoverpoint.com.au ¦ Free to use ¦ Status: Pending / Submitted / Approved / Rejected
Item | Trade | Spec Reference | Product / Manufacturer | Status | Submitted Date | Approved Date | Location of Sample | Notes
1 | Tiling | 09 30 00 | Porcelain floor tile, 600x600, Brand X | Approved | 2026-01-14 | 2026-01-22 | Site office, sample board A | Matt finish confirmed
2 | Joinery | 06 40 00 | Laminate benchtop, Colour Y | Submitted | 2026-02-03 |  | With architect | Awaiting review
3 | Windows | 08 50 00 | Aluminium window suite, Series Z | Rejected | 2026-02-10 |  | Returned to supplier | Wrong glazing spec, resubmit
4 | Painting | 09 90 00 | Interior low-sheen, Colour ref TBC | Pending |  |  | Not yet submitted | Colour schedule due

## Instructions
How to use this Sample Register
A sample and submittal register tracks every product sample, prototype or technical submission through review and approval. Add one row per item and update the status as it moves. The four greyed rows are worked examples, overwrite or delete them.
Columns
Item | A reference number for the sample.
Trade | The trade or package the sample belongs to, e.g. Tiling, Joinery, Windows.
Spec Reference | The specification section that calls up the product.
Product / Manufacturer | The product name and manufacturer being submitted.
Status | One of Pending, Submitted, Approved or Rejected.
Submitted Date | The date the sample was submitted for review.
Approved Date | The date the sample was approved. Leave blank until approved.
Location of Sample | Where the physical sample sits, e.g. sample board, site office, with the architect.
Notes | Any comment: revision, reason for rejection, or next action.
Status values
Pending | Identified but not yet submitted for review.
Submitted | Sent for review and awaiting a decision.
Approved | Accepted and cleared for use on the project.
Rejected | Not accepted. Note the reason and resubmit a compliant sample.
HandoverPoint
Generate this register automatically from your spec at handoverpoint.com.au